## PROJECT
COMMUNICATIONS MANAGEMENT PLAN
PROJECT DETAILS
PROJECT No: | MA-015-02
DATE:
FULL PROJECT NAME: | Project Agile
PROJECT MANAGER: | A Oseni
PROJECT SPONSOR: | A Oseni

## COMMUNICATIONS MANAGEMENT PLAN
COMMUNICATIONS MANAGEMENT PLAN
ID | STAKEHOLDER | INFORMATION | METHOD | TIMING OR FREQUENCY | SENDER | ASSUMPTIONS | CONSTRAINTS
S001 | Call centre agents | High level information on go live, new features and training dates. | Email and verbal updates via team leads. | Monthly until rollout phase then weekly. | Project Manager / Change Manager | All Spanish speaking call centre agents are able to read English up to college level. Team leads will provide verbal updates via meetings. | Email must be plain text, max size attachments is 2mb.
S002 | IT support and infra team | Tech spec and hardware requirements. Go live dates and pen test results. | Email and IT weekly mtg at key milestones. | To align with start up, test and prep for launch. | Project Manager | None. | Max size attachments is 2mb.
S003 | Marketing | New features for users so marketing can write website blurb. | Email product brief, and arrange meeting with marketing manager. | Dates tbc | Change Manager | Assumes that new product launches will have been completed, so marketing has bandwidth for website update. | Website update must not fall during holiday change freeze.
S004 | Customers | Coming soon update on new features and go live help text. Provide in English and Spanish. | Email and on website | Dates tbc | Change Manager | Assumes 60% of emails will get through and remainder of users can self-assist using help text. | Help text must be screen reader compatible.

## DEFINITIONS
DEFINITIONS
PROJECT MANAGER
The person with responsbility for managing and delivering the project. They will own this log, but may not be the person maintaining it.
PROJECT ID
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
PROJECT SPONSOR
The person with ultimate accountablity for the project. They will hold the purse strings.
PROJECT TITLE
The name of the project, this should align with the name given on other project documents (rather than being a nickname).
STAKEHOLDER ID
Give each stakeholder a unique identifier or reference so that it can be easily traced.
STAKEHOLDER
Enter the name of the stakeholder or stakeholder group.
INFORMATION
Give as much detail as you can about the information that the stakeholder/group needs to receive. For example, 'High level information on go live, new features and training dates. '
METHOD
Describe how the information will be communicated. For example, email, meetings, website updates, events etc.
TIMING OR FREQUENCY
Describe when and how often the information will be communicated. For some stakeholders a regular update may be needed for others it may be a one off tied to an event. For example, notification of a new system going online with key technical information for a network support team.
SENDER
Give the person who will be responsible for making sure the communication is sent. This might not necessarily be the person who writes the email or delivers a presentation, but will be the person who makes the arrangements.
ASSUMPTIONS
Include any assumptions that you have made about the communication. For example that new website pages will be available or that assets for the comms will be ready e.g. a new logo. It is worth noting any assumptions you have made about the comms being successfully recieved. For example, it might be that you are assuming all users have email access. You might also be assuming that spam filters will not be a problem. Or you may assume that all recipients can read English to a particular level.
CONSTRAINTS
Enter any factors that constrain the communication. For example, a date by which it must be delivered, or a max file size for email.

## CUSTOMISE
HOW TO CHANGE THE MENU ITEMS IN STATUS FIELDS
Default settings
We have not set any drop down menus, as it is likely that most projects will have different priorities and categories.
How to create a drop down menu
Click on Data tab > Data Validation > Settings > List
In the Source field enter the menu items separated by a comma.
To change the menu items
To change the menu options or remove the dropdown select Data > Data Validation > Settings > List
ADDITIONAL FIELDS YOU MIGHT WANT TO ADD
Actions - A column for any actions related to the communication or to manage an assumption.
Task ID/WBS ID - To record any associated tasks on the project schedule.
Risk ID - a look up to any associated risks.
Budget/costs estimate
Project ID - For large communications efforts you may have a separate project. For example there might be a project to translate comms into other languages.
Dependencies - Some comms may be dependent on other tasks being completed.
Approval/Sign-off - To record the person/group who has authority to approve the communication before it is sent.